## Summary
Pioneer Auctions delivery plan
Engineering implementation estimate based on weighted task acceptance criteria. Updated 2026-09-14 from branch agent/task-006-mobile-buyer-loop.
Metric | Current value
Estimated engineering completion | 56.07%
Fully complete task packets | 3
Tasks active or in rework | 4
Tasks not started | 5
Current repository head | ed178c3
Current position | Assessment
Completed foundation | Tasks 001–003: monorepo, executable contracts and cross-platform design/localization foundation.
Strongest implemented core | Task 004 bidding engine and Task 007 admin operations have substantial real PostgreSQL verification.
Active buyer work | Web is advanced but incomplete. Mobile has a strong visual prototype and is undergoing safety-critical integration repair.
Largest remaining blocks | Production identity/KYC, financial ledger/payments, notifications, observability/load proof and controlled test auction.
Percentage interpretation | The percentage measures planned engineering effort completed. It is not a launch-readiness claim; critical go-live gates remain open.
Next five priorities | Owner
Close all Task 006 critical/high mobile review findings | Antigravity
Finish Task 004 crash/recovery and operational proof | Backend owner
Complete identity sessions, KYC adapters and admin step-up | Identity owner
Implement dummy payment provider on a balanced replay-safe ledger | Payments owner

## Task Plan
Task plan and completion
Task completion rolls up from effort-weighted rows in Detailed Backlog. Task weights total 100%.
Task ID | Task | Workstream | Plan weight | Owner | Completion | Weighted contribution | Status | Done | What remains | Dependencies | Next action | Branch / evidence
001 | Monorepo and local foundation | Foundation | 5% | Codex | 100% | 5% | Complete | Monorepo, apps, shared configuration, local services, CI, health and logging. | Docker runtime validation remains environment-dependent. | None | Keep dependencies and CI pins current. | agent/task-001-foundation
002 | Runtime contracts and compatibility | Contracts | 7% | Codex | 100% | 7% | Complete | Zod contracts, OpenAPI, Socket.IO maps, fixtures, Dart generation and drift checks. | Maintain synchronized docs, schemas and generated artifacts. | 001 | Treat contracts as the source for every client change. | agent/task-002-runtime-contracts
003 | Design system and localization foundation | Design system | 8% | Antigravity | 100% | 8% | Complete | Shared tokens, web and Flutter primitives, RTL foundations, light/dark semantics and accessibility rules. | Official master logo and native Arabic review are still external dependencies. | 001 | Apply the system consistently while rebuilding product screens. | agent/task-003-design-system
004 | Atomic bidding engine and close orchestration | Backend core | 18% | Claude Code / backend owner | 88.75% | 15.97% | In progress | Manual and proxy bidding, PostgreSQL serialization, idempotency, soft-close, outbox, recovery and lifecycle scheduling exist. | Complete kill-point proof, Redis recovery integration, metrics and final technical acceptance. | 001, 002 | Close remaining correctness and operability gates. | agent/task-004-backend-week1
005 | Next.js buyer loop | Buyer web | 12% | Antigravity | 73.67% | 8.84% | In progress | Discovery, lot detail, REST bidding, proxy logic, realtime recovery foundation, search/calendar and Cloudflare preview exist. | Finish full account activity, complete gates and fee UX, Arabic/accessibility verification and end-to-end journeys. | 002, 003, 004 | Complete live buyer journey and browser automation. | Implemented on agent/task-007-admin-core
006 | Flutter mobile buyer loop | Mobile | 12% | Antigravity | 32.79% | 3.935% | Rework in progress | Ten-screen Android UI, shared Dart contracts and initial REST/realtime adapters exist. REST alignment fix committed at ed178c3. | Resolve realtime protocol, false-success bidding, recovery, proxy/gates, full localization, accessibility, dark mode, iOS and live integration tests. | 002, 003, 004 | Finish all review findings before claiming completion. | agent/task-006-mobile-buyer-loop
007 | Admin auction operations | Admin | 10% | Antigravity / Codex | 55.58% | 5.558% | In progress | Dashboard, lot and auction operations, final-bid decisions, audit reads, bulk import and live database validation exist. | Step-up auth, permission-aware UI, realtime monitor, deposit/offer/consignment queues and Playwright journeys remain. | 002, 003, 004 | Complete high-risk operations and missing queues. | agent/task-007-admin-core
008 | Identity, UAE PASS and fallback KYC | Identity | 8% | Backend integration owner | 5.417% | 0.4333% | Not started | Basic account/session/RBAC development foundation exists in the API. | UAE PASS OIDC/PKCE, refresh sessions, revocation, OTP fallback, KYC state machine, encryption, step-up auth and security tests. | 001, 002 | Start provider-independent session and fake KYC adapters. | Unassigned
009 | Deposits, payments, refunds and ledger | Payments | 8% | Backend payments owner | 8.6% | 0.688% | Not started | Dummy-payment direction and early admin/payment scaffolding exist. | Balanced ledger, policy rules, hosted checkout, replay-safe webhooks, refunds, reconciliation, client return flows and finance views. | 001, 002, 008 | Implement dummy provider and ledger invariants first. | Unassigned
010 | Transactional notifications | Notifications | 5% | Codex | 3% | 0.15% | Not started | Domain events and outbox foundations can feed future notification intents. | Notification ledger, templates, preferences, push/email adapters, reminders, dedupe, retries and in-app feed. | 002, 004, 008 | Build development sinks and deduplicated notification intents. | Unassigned
011 | Observability, load and runbooks | Operations | 4% | Codex with SRE review | 12.14% | 0.4857% | Not started | Structured logs, correlation IDs and OpenTelemetry foundations exist. | Dashboards, alerts, load harness, failure injection, capacity proof and executable runbooks. | 004, 008, 009 | Define target load and instrument bid/outbox/payment paths. | Unassigned
012 | MVP hardening and test auction | Release | 3% | Product owner and all owners | 0% | 0% | Not started | No release gate has been completed yet. | Security/legal/finance/Arabic/accessibility reviews, migration and recovery rehearsals, controlled auction, reconciliation and go/no-go. | 004–011 | Begin only after upstream MVP scopes are accepted. | Unassigned
| Total |  | 100% |  | 56.07% | 56.07%

## Detailed Backlog
Detailed implementation backlog
Effort points are relative within each task. Completion is a conservative evidence-based estimate, not elapsed time.
Task ID | Workstream | Detailed deliverable | Effort points | Completion | Status | What is done | What remains | Dependency | Priority
001 | Foundation | Generate NestJS, buyer web and admin apps | 2 | 100% | Complete | Apps scaffolded and buildable. | Maintain framework pins. | None | P2
001 | Foundation | Configure pnpm workspace, Turborepo and lockfile | 1 | 100% | Complete | Workspace and build ordering established. | Maintain clean install support. | None | P2
001 | Foundation | Create PostgreSQL, Redis, MinIO and Mailpit local services | 2 | 100% | Complete | Compose services and health checks defined. | Keep Docker validation documented. | Docker | P2
001 | Foundation | Implement liveness, readiness and dependency checks | 1 | 100% | Complete | Health endpoints distinguish liveness/readiness. | Extend as providers are added. | API scaffold | P2
001 | Foundation | Add structured logging, correlation IDs and OpenTelemetry base | 1 | 100% | Complete | Baseline observability exists. | Add domain metrics in Task 011. | API scaffold | P2
001 | Foundation | Add CI, secret scan and dependency audit | 2 | 100% | Complete | Pull-request quality gates exist. | Keep checks aligned with Flutter and new providers. | Workspace | P2
002 | Contracts | Define money, time, UUID, error and lifecycle schemas | 2 | 100% | Complete | Zod v1 primitives exist. | Version breaking changes. | 001 | P1
002 | Contracts | Define bid, proxy and snapshot commands and acknowledgements | 2 | 100% | Complete | Executable schemas and fixtures exist. | Maintain parity during implementation. | 001 | P1
002 | Contracts | Define public and personal realtime events | 2 | 100% | Complete | Flat lot events and enveloped personal events aligned. | Prevent event drift. | 001 | P1
002 | Contracts | Generate OpenAPI and JSON Schema | 1 | 100% | Complete | Generated artifacts committed and checked. | Regenerate on changes. | Schemas | P2
002 | Contracts | Generate Dart models and golden decode proof | 2 | 100% | Complete | Flutter can consume shared fixtures. | Add mobile runtime validation wrappers. | Schemas | P1
002 | Contracts | Add additive/breaking compatibility policy | 1 | 100% | Complete | Version rollout policy recorded. | Apply to all future changes. | Schemas | P2
003 | Design system | Create canonical tokens and generated CSS/Dart outputs | 2 | 100% | Complete | Cross-platform token foundation exists. | Prevent downstream token forks. | 001 | P2
003 | Design system | Implement semantic light and dark themes | 2 | 100% | Complete | Theme semantics and contrast checks established. | Apply dark theme to product screens. | Tokens | P2
003 | Design system | Implement shared web primitives | 2 | 100% | Complete | Core interactive and auction primitives exist. | Use consistently in buyer/admin refresh. | Tokens | P2
003 | Design system | Implement Flutter primitives and component gallery | 2 | 100% | Complete | Flutter primitive foundation exists. | Align Task 006 custom widgets to canonical tokens. | Tokens | P2
003 | Design system | Establish Inter and Tajawal typography | 1 | 100% | Complete | Fonts and pairing selected. | Verify Arabic production rendering. | Brand | P2
003 | Design system | Establish RTL, bidi, reduced-motion and accessibility rules | 2 | 100% | Complete | Rules and fixtures documented. | Verify every product screen. | Tokens | P1
003 | Design system | Obtain official production logo and native Arabic signoff | 1 | 100% | Complete | Provisional asset and signoff requirement recorded. | Replace provisional logo when supplied. | Brand owner | P3
004 | Backend core | Create auction, lot, bid, proxy, terms and eligibility migrations | 3 | 100% | Complete | Durable PostgreSQL models exist. | Review forward migrations before production. | 001,002 | P1
004 | Backend core | Implement atomic manual bid decision | 4 | 100% | Complete | PostgreSQL row lock serializes same-lot bids. | Maintain invariant tests. | Persistence | P0
004 | Backend core | Implement proxy maximum and deterministic tie resolution | 4 | 100% | Complete | Raise-only proxy policy and automatic responses verified. | Maintain privacy and tie tests. | Manual bidding | P0
004 | Backend core | Implement command idempotency and ordered per-lot ledger | 3 | 100% | Complete | Repeated commands preserve original outcome. | Keep command ledger append-only. | Persistence | P0
004 | Backend core | Implement reserve transition and configurable soft close | 3 | 100% | Complete | Two-minute defaults and per-lot overrides implemented. | Add operational monitoring. | Bid decision | P0
004 | Backend core | Implement REST and Socket.IO bidding commands | 3 | 95% | In progress | REST and gateway foundations work with shared service. | Complete production session/auth integration. | Identity adapter | P0
004 | Backend core | Implement transactional outbox, replay and personal events | 3 | 95% | In progress | Durable publish/replay and private status fanout exist. | Finish backlog monitoring and failure proof. | Persistence | P0
004 | Backend core | Implement open/close scheduler fencing | 3 | 90% | In progress | Lifecycle scheduler and close worker exist. | Prove multi-instance operation and operational controls. | Bid decision | P0
004 | Backend core | Rebuild Redis-derived state from PostgreSQL | 3 | 65% | In progress | Recovery service abstraction exists. | Connect real Redis store and rehearse loss/failover. | Redis | P0
004 | Backend core | Run kill-point, multi-lot and failure-injection proof | 3 | 35% | In progress | Real DB race and soft-close tests pass. | Complete crash points, non-global serialization and archived evidence. | Operations | P0
005 | Buyer web | Home, categories and public discovery | 2 | 90% | In progress | Responsive preview and backend-shaped lots exist. | Complete production content and loading/error states. | API lots | P1
005 | Buyer web | Search, filters and auction calendar | 2 | 85% | In progress | Search/filter/calendar shells and tests exist. | Finish full category facets and saved searches. | Catalog | P2
005 | Buyer web | Lot detail, gallery, documents and public metadata | 3 | 85% | In progress | SSR lot detail and SEO metadata exist. | Complete media/documents and fee presentation. | Catalog | P1
005 | Buyer web | Manual/custom bid state machine | 4 | 90% | In progress | Accepted/rejected/unknown states and REST command path exist. | Finish live session and end-to-end browser proof. | 004,008,009 | P0
005 | Buyer web | Realtime subscription, reconnect and gap recovery | 4 | 90% | In progress | Socket client tests cover reconnect and sync. | Verify against production-like gateway deployment. | 004 | P0
005 | Buyer web | Proxy maximum setup and status | 3 | 85% | In progress | Raise-only proxy interactions exist and were live verified. | Complete user-facing recovery and expiry states. | 004 | P0
005 | Buyer web | Terms, eligibility, deposit and fee confirmation gates | 3 | 60% | In progress | State shells and adapters exist. | Connect Tasks 008–009 and show total payable cost. | 008,009 | P0
005 | Buyer web | Watchlist, My Bids and post-close status | 3 | 50% | In progress | Partial shells/interactions exist. | Build authenticated persistence and approval/payment next steps. | 008,009 | P1
005 | Buyer web | Arabic RTL, dark mode and accessibility | 3 | 65% | In progress | RTL and localized shell foundation exists. | Complete real Arabic copy, keyboard and screen-reader audit. | 003 | P1
005 | Buyer web | Automated end-to-end buyer journeys | 3 | 35% | In progress | Unit and integration tests exist. | Add Playwright journeys against live API/database. | All buyer dependencies | P0
006 | Mobile | Android Flutter application scaffold | 1 | 100% | Complete | Android project and debug build exist. | Maintain release configuration. | 003 | P2
006 | Mobile | Ten buyer screens and navigation | 3 | 90% | In progress | High-fidelity screens and routes exist. | Replace static/mock behavior with real state and accessibility. | Design system | P1
006 | Mobile | Reusable auction mobile components | 2 | 80% | In progress | Cards, chips, header, nav and slide control exist. | Align authoritative states, RTL and semantics. | Design system | P1
006 | Mobile | REST authentication, idempotency and public lot decoding | 3 | 75% | In progress | Alignment fix committed at ed178c3. | Verify against live NestJS and valid seed UUIDs. | API, session | P0
006 | Mobile | Contract-correct Socket.IO events and acknowledgements | 4 | 30% | Rework in progress | Socket rewrite is present as uncommitted work during this audit. | Finish real event names, validation, acknowledgements and tests. | 004 | P0
006 | Mobile | Authoritative bid state and no false success | 4 | 15% | Rework in progress | Critical review finding identified. | Remove simulated acceptance; support accepted/rejected/unknown reconciliation. | REST/socket | P0
006 | Mobile | Reconnect, sequence gaps, snapshots and foreground sync | 4 | 10% | Rework in progress | Not present in reviewed commits. | Implement retained subscription, dedupe, gap sync and lifecycle observer. | Socket state | P0
006 | Mobile | Proxy bidding, terms, eligibility and fee confirmation | 4 | 5% | Not started | Static visual elements only. | Implement contract-backed proxy and pre-bid gates. | 004,008,009 | P0
006 | Mobile | Complete English/Arabic localization and bidi safety | 3 | 25% | Rework in progress | Locale switch exists; most screens remain hardcoded English. | Move every visible string and test real RTL content. | 003 | P1
006 | Mobile | Dark mode, large text, reduced motion and screen readers | 3 | 15% | Not started | Some safe-area and visual component work exists. | Implement theme mode and accessibility state matrix. | 003 | P1
006 | Mobile | iOS project and platform validation | 2 | 0% | Not started | No iOS scaffold in reviewed implementation. | Generate iOS platform files; validate later on macOS/Xcode. | Apple toolchain | P1
006 | Mobile | Push and hosted-payment return routing stubs | 1 | 0% | Not started | No routing stubs found. | Add Task 009/010 deep-link contracts. | 009,010 | P2
007 | Admin | Operations dashboard and protected read models | 2 | 90% | In progress | Dashboard and API-backed adapter exist. | Remove fallback ambiguity in authenticated runtime. | API auth | P1
007 | Admin | Lot create/edit and increment/soft-close configuration | 3 | 90% | In progress | Create and safe partial edit flows exist. | Define money/increment editing after bidding starts. | Product decision | P1
007 | Admin | Auction create/edit/pause/resume/cancel | 3 | 90% | In progress | Commands live-verified against PostgreSQL. | Add step-up auth and operational rehearsal. | 008 | P0
007 | Admin | Final-bid approve/reject without hammer mutation | 3 | 95% | In progress | Decision paths and audit entries exist. | Add SLA views and step-up authentication. | 008 | P0
007 | Admin | Transactional bulk lot import | 2 | 95% | In progress | Dry-run, validation and atomic commit exist. | Add file upload workflow and larger fixtures if required. | Catalog | P1
007 | Admin | Immutable audit trail read experience | 2 | 90% | In progress | Protected audit endpoint and UI exist. | Add filtering, retention policy and export as approved. | Audit | P1
007 | Admin | Permission-aware UI | 2 | 20% | Not started | Server permissions exist. | Expose safe current-session permissions and hide unauthorized actions. | 008 | P1
007 | Admin | Step-up authentication for high-risk actions | 3 | 0% | Not started | No step-up mechanism exists. | Implement through Task 008 and bind to approvals/finance/control actions. | 008 | P0
007 | Admin | Realtime live auction monitor and gap recovery | 3 | 0% | Not started | No admin realtime namespace exists. | Define and implement admin monitor contract. | 004 | P0
007 | Admin | Offer, consignment and deposit operations queues | 3 | 10% | Not started | Final-bid queue exists; other domains are absent. | Build underlying domain models/endpoints before UI. | 008,009 | P1
008 | Identity | Account, RBAC and development session foundation | 2 | 50% | In progress | Basic account lookup, roles and permissions exist. | Replace test-header runtime with production sessions. | 001,002 | P0
008 | Identity | Short-lived access and rotating refresh sessions | 3 | 0% | Not started | No production token/session lifecycle. | Implement rotation, revocation and replay detection. | Security design | P0
008 | Identity | UAE PASS OIDC authorization code with PKCE | 4 | 0% | Not started | Provider onboarding remains external. | Build adapter using official staging evidence. | UAE PASS access | P0
008 | Identity | OTP fallback and development fake provider | 2 | 0% | Not started | No OTP provider abstraction. | Implement provider interface, rate limits and safe fake. | Security design | P1
008 | Identity | Fallback KYC state machine and webhook contract | 4 | 0% | Not started | No provider-independent KYC lifecycle. | Implement verified state transitions and replay-safe webhook. | Provider decision | P0
008 | Identity | Field classification, encryption and minimal identity mapping | 3 | 10% | Not started | Security rules documented only. | Implement storage controls without raw provider payloads. | Legal/security | P0
008 | Identity | Admin step-up authentication hooks | 3 | 0% | Not started | Required by Task 007 and finance actions. | Implement challenge/evidence/audit model. | Sessions | P0
008 | Identity | Identity and session security test matrix | 3 | 0% | Not started | No OIDC/session replay suite. | Test forgery, nonce/state mismatch, revocation and outage recovery. | All identity work | P0
009 | Payments | Deposit requirement policy and overrides | 2 | 20% | Not started | Product defaults discussed; full policy service absent. | Implement global/category/auction/lot resolution. | Product decision | P1
009 | Payments | Append-only balanced financial ledger | 4 | 10% | Not started | Early database/payment scaffolding only. | Implement entries, balances and invariant tests. | Finance approval | P0
009 | Payments | Dummy hosted checkout provider | 3 | 20% | Not started | Dummy gateway selected for development. | Build provider adapter and deterministic success/failure scenarios. | Ledger | P0
009 | Payments | Replay-safe signed webhook inbox | 4 | 0% | Not started | No production webhook state machine. | Implement verification, dedupe, reordering and retries. | Provider contract | P0
009 | Payments | Deposit eligibility updates | 3 | 15% | Not started | Eligibility models exist in bidding foundation. | Update only from authoritative cleared payment state. | Ledger,004 | P0
009 | Payments | Refund workflow, SLA timeline and receipts | 3 | 0% | Not started | No refund lifecycle. | Implement request, approval, processing and compensation. | Finance rules | P0
009 | Payments | Daily reconciliation and exception queue | 3 | 0% | Not started | No provider reconciliation. | Build provider-versus-ledger report and unresolved queue. | Provider data | P0
009 | Payments | Web/mobile return and admin finance views | 3 | 10% | Not started | UI shells only. | Connect hosted return, deposit ledger and finance actions. | 005,006,007 | P1
010 | Notifications | Notification intent/outbox and dedupe model | 3 | 15% | Not started | Domain outbox foundation exists. | Add user/channel/template dedupe and retries. | 004 | P0
010 | Notifications | English and Arabic transactional templates | 3 | 0% | Not started | Notification matrix documented. | Implement versioned templates and native Arabic review. | Product copy | P1
010 | Notifications | FCM/APNs or OneSignal provider adapter | 3 | 0% | Not started | No push provider connected. | Implement development sink first, then approved provider. | Provider decision | P1
010 | Notifications | Email adapter and development sink | 2 | 0% | Not started | Mailpit exists locally. | Implement templated delivery and receipts. | 001 | P2
010 | Notifications | In-app feed and deep links | 3 | 5% | Not started | Event/deep-link contracts exist. | Build grouped feed and routing across web/mobile. | 005,006 | P1
010 | Notifications | Preferences, quiet hours and marketing separation | 3 | 0% | Not started | Policy described only. | Implement consent-aware channel/category controls. | Legal review | P0
010 | Notifications | Ending and upcoming reminder scheduler | 3 | 0% | Not started | No notification scheduler. | Support cancellation and soft-close rescheduling. | 004 | P1
011 | Operations | Trace HTTP, sockets, bidding, DB, outbox and providers | 3 | 25% | Not started | HTTP/logging/OpenTelemetry base exists. | Add domain spans with privacy controls. | 004,008,009 | P1
011 | Operations | Operational metrics and dashboards | 3 | 10% | Not started | Some structured telemetry fields exist. | Build bid/outbox/close/payment/notification dashboards. | Instrumentation | P0
011 | Operations | Alert ownership and runbook links | 2 | 0% | Not started | No production alert set. | Define severities, owners and user impact. | Dashboards | P1
011 | Operations | Reproducible concurrency/load harness | 4 | 20% | Not started | 100-command DB race test exists. | Model sockets, lots, proxies, bursts and reconnects. | 004 | P0
011 | Operations | Failure injection and recovery rehearsal | 4 | 10% | Not started | Recovery unit foundations exist. | Kill gateway/worker, restart Redis and inject DB/provider failures. | 004,009 | P0
011 | Operations | Auction operations and incident runbooks | 3 | 10% | Not started | Runbook locations planned. | Write and execute go/no-go, replay and communication steps. | All services | P0
011 | Operations | Capacity headroom and scaling thresholds | 2 | 0% | Not started | Architecture target documented. | Measure and define triggers for sharding/search extraction. | Load evidence | P1
012 | Release | Close all critical and high defects | 4 | 0% | Not started | Task 006 currently has open critical/high findings. | Maintain release-blocker list until zero unresolved. | 004–011 | P0
012 | Release | Security threat model and dependency checks | 3 | 0% | Not started | Baseline scans exist only. | Complete threat model, admin role and retention review. | 008,009 | P0
012 | Release | English/Arabic and accessibility signoff | 3 | 0% | Not started | Foundations exist; production review absent. | Native Arabic review and full accessibility audit. | 003,005,006,007 | P0
012 | Release | Migration, backup, restore and deployment rehearsal | 4 | 0% | Not started | No production infrastructure rehearsal. | Exercise migration, restore, rollback and secret rotation. | 011 | P0
012 | Release | Internal synthetic auction | 4 | 0% | Not started | No complete integrated environment. | Run all buyer/admin/payment/notification paths. | 004–011 | P0
012 | Release | Invited controlled test auction and reconciliation | 5 | 0% | Not started | No test auction completed. | Measure latency, outcomes, ledgers and incident response. | Synthetic auction | P0
012 | Release | Signed go/no-go and MVP readiness evidence | 3 | 0% | Not started | Release evidence document absent. | Collect legal, finance, security, Arabic and owner signoffs. | All gates | P0

## Technology Stack
Technology stack
Current repository technologies and planned production integrations. Versions reflect the audited workspace on 2026-09-14.
Layer | Capability | Technology | Version / choice | Status | Purpose | Notes / remaining work
Repository | Monorepo | pnpm workspaces + Turborepo | pnpm 11.4.0; Turbo 2.10.5 | Installed | Shared builds, tests and packages | Keep Flutter checks explicitly integrated with CI
Runtime | Node.js | Node.js LTS | 24.18.x | Installed | API, web, admin and build tooling | Pinned to >=24.18 <25
Mobile | Framework | Flutter / Dart | Flutter 3.47.3; Dart 3.13.3 | In progress | Android and iOS buyer application | Android exists; iOS and complete live behavior remain
Mobile | Navigation | go_router | 18.0.1 | Installed | Deep-linkable application routing | Push/payment return stubs remain
Mobile | Networking | http + socket_io_client | http 1.2.1; Socket.IO client 3.0.1 | Rework in progress | REST and realtime bidding | Contract alignment under active repair
Mobile | Localization | Flutter localizations + intl | intl 0.20.3 | Partial | English/Arabic and RTL | Most visible strings still require localization
Buyer web | Framework | Next.js / React / TypeScript | Next 16.2.10; React 19.2.7; TS 5.9.3 | In progress | SSR lot discovery and full bidding client | Cloudflare preview deployed
Admin | Framework | Next.js / React / TypeScript | Next 16.2.10; React 19.2.7; TS 5.9.3 | In progress | Protected auction operations console | Cloudflare preview deployed
Backend | Framework | NestJS / Express | NestJS 11.1.28; Express 5.2.1 | In progress | Modular API and Socket.IO gateway | Modular monolith
Backend | Realtime | Socket.IO | 4.8.1 | In progress | Commands, acknowledgements and room fanout | Namespace /auctions/v1
Backend | Validation/contracts | Zod | 4.4.3 | Complete foundation | Runtime schemas and transport validation | Source for generated schemas
Data | Durable database | PostgreSQL | Local Compose 17; pg 8.22.0 | In progress | Auction, bid, identity and financial ledgers | Authoritative durable state
Data | Realtime cache | Redis | Local Compose 8; client 6.1.0 | Partial | Derived live state, coordination and fanout | Must remain recoverable from PostgreSQL
Data | Object storage | MinIO locally; AWS S3 planned | MinIO 2025-09-06 | Foundation | Images, videos and documents | Production malware scanning/presigned flows remain
Search | Search engine | PostgreSQL initially; OpenSearch planned | Not provisioned | Planned | Full-text and faceted lot discovery | Add only when MVP scale requires it
Contracts | Shared transport | @pioneer/contracts | Contract v1 | Complete foundation | TypeScript, OpenAPI, JSON Schema and Dart models | Compiled ESM dist required before standalone Next builds
Design | Tokens and fonts | Shared tokens; Inter; Tajawal | Inter 5.2.8; Tajawal 5.2.7 on web | Complete foundation | Brand, semantic states and RTL typography | Native Arabic review remains
Testing | TypeScript | Vitest | 4.1.10 | Active | Unit, contract, DB integration and race tests | Playwright journeys remain absent
Testing | Flutter | flutter_test | Flutter SDK | Active | Widget and unit tests | Real gateway trace and iOS validation remain
Observability | Telemetry | OpenTelemetry + Pino | OTel API 1.9.1; Pino 10.3.1 | Foundation | Logs, traces and correlation IDs | Dashboards, alerts and load evidence remain
Local development | Email sink | Mailpit | 1.30.4 | Installed | Development email capture | Notification adapter remains
Deployment | Preview hosting | Cloudflare Workers | Wrangler 4.120.1 | Active preview | Buyer web, admin and preview API | Not the planned production backend
Deployment | Production target | AWS ECS/Fargate, RDS, ElastiCache, S3, CloudFront/WAF | Not provisioned | Planned | Regional production platform | Infrastructure as code remains
Identity | Primary provider | UAE PASS OIDC/PKCE | Not integrated | Planned | Verified UAE onboarding and identity | Staging/commercial onboarding required
Identity | Fallback KYC | Provider abstraction; vendor TBD | Not integrated | Planned | Non-UAE-PASS bidder verification | Do not hardcode provider behavior
Payments | Development gateway | Dummy provider | Not implemented | Planned next | Deterministic testing without real charges | Must still use replay-safe ledger/webhooks
Payments | Production gateway | Network International N-Genius primary; Telr/Checkout.com fallback | Not integrated | Planned | AED deposits and purchase payments | Commercial approval required
Notifications | Push | FCM/APNs, possibly OneSignal orchestration | Not integrated | Planned | Transactional push and campaigns | Provider decision and consent rules remain

## Roadmap
MVP execution roadmap
Sequenced from the current mobile repair through a controlled test auction. Dates depend on external provider approvals and review capacity.
Sequence | Milestone | Timing | Scope | Exit criterion | Owner | Priority
1 | Stabilize current mobile branch | Now | Fix Task 006 review findings, finish realtime recovery, remove false bid success and commit cleanly. | All critical/high mobile findings closed; live contract trace passes. | Antigravity | P0
2 | Accept bidding engine | Next | Finish Redis recovery connection, kill-point proof, multi-instance behavior and correctness handoff. | Task 004 acceptance criteria pass with archived evidence. | Backend owner | P0
3 | Complete buyer web and admin gaps | Next | Finish account activity, gates, fee UI, step-up integration, missing queues and browser journeys. | Tasks 005 and 007 accepted. | Antigravity | P0
4 | Build identity and KYC foundation | After core bidding | Implement production sessions, fake providers, UAE PASS adapter boundary, KYC lifecycle and admin step-up. | Task 008 security matrix passes. | Backend integration owner | P0
5 | Build dummy payments and financial ledger | Parallel after identity model | Implement balanced ledger, dummy hosted checkout, webhook inbox, refunds and eligibility events. | Task 009 ledger and replay tests pass. | Payments owner | P0
6 | Build transactional notifications | After stable domain events | Create intents, localized templates, development sinks, preferences and reminders. | Task 010 dedupe and scheduler tests pass. | Codex | P1
7 | Production observability and load proof | After integrated journeys | Instrument, load test, inject failures and execute auction runbooks. | Task 011 targets and recovery evidence accepted. | Codex / SRE | P0
8 | Controlled test auction | Final MVP gate | Run synthetic then invited auction with reconciliation, accessibility, Arabic, legal, finance and security review. | Signed go/no-go and reconciled release evidence. | Product owner | P0

## Risks and Links
Risks, environments and links
Open delivery risks and current shared preview endpoints. No production environment exists yet.
Risk ID | Risk | Severity | State | Mitigation / next action | Owner | Related work
R-001 | Mobile may show rejected/timeout bids as accepted | Critical | Open; repair in progress | Remove simulation; authoritative state machine; same-command reconciliation | Antigravity | Task 006
R-002 | Mobile realtime contract and reconnect handling incomplete | High | Open; uncommitted rewrite observed | Validate real event names; acknowledgements; sequence dedupe/gap sync; foreground recovery | Antigravity | Task 006
R-003 | Identity and KYC are not production-ready | Critical | Not started | Start provider-independent sessions/KYC and UAE PASS onboarding | Identity owner | Task 008
R-004 | No balanced financial ledger or replay-safe payment flow | Critical | Not started | Build dummy provider only after ledger/inbox invariants | Payments owner | Task 009
R-005 | Admin high-risk actions lack step-up authentication | High | Open | Implement Task 008 step-up and bind to approvals/finance/control commands | Identity/Admin owners | Tasks 007–008
R-006 | No production-like load/failure evidence | High | Open | Build load harness, inject failures and archive results | SRE owner | Task 011
R-007 | Arabic copy and critical RTL paths lack native signoff | High | Open | Complete localization then obtain native Arabic QA approval | Product/QA | Tasks 005–007,012
R-008 | Current UI direction may require later redesign | Medium | Deferred by product owner | Keep behavior/components modular; schedule a focused design review | Product/Design | Post-core stabilization
R-009 | Current state documentation is stale during parallel work | Medium | Open | Update canonical state at every clean task handoff | All owners | Repository process
R-010 | UAE PASS and production gateway onboarding can gate launch | High | External dependency | Start approvals early; keep provider adapters and approved fallback path | Product owner | Tasks 008–009
Resource | URL | Purpose
GitHub repository | https://github.com/Maazkhan88/Pioneer-Auctions | Source repository
Buyer web preview | https://pioneer-auctions-web.maaz-n-khan.workers.dev | Remote buyer UI preview
Admin preview | https://pioneer-auctions-admin.maaz-n-khan.workers.dev | Remote admin UI preview
Preview API | https://pioneer-auctions-api.maaz-n-khan.workers.dev | Dummy/public preview API
Active mobile branch | https://github.com/Maazkhan88/Pioneer-Auctions/tree/agent/task-006-mobile-buyer-loop | Task 006 source